## Strategic Priorities
Richland County Strategic Priorities
Effectiveness | Implement operational efficiencies to reduce the costs and free up revenue
Growth | Work to increase the county's population and tax base in order to fund services
Focus | Scale back or eliminate discretionary services that cannot provide sustainable revenue to cover their costs
Improvement | Create a culture of continual improvement to sustain progress

## Operations
LAST UPDATE: [INSERT DATE]
STRATEGIC PRIORITY: EFFECTIVENESS
STRATEGY | TACTIC / ACTION | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Streamline Organizational Structure | Centralize common county-wide processes and systems under the County Administrator. |  | Project Implemented
| Create county-wide organizational chart |  | Project Implemented
| Create a finance, HR, and maintenance department |  | Project Implemented
| Improve the county’s procurement process to be consistent county-wide. Maximize procurement rewards or benefits and identify joint procurement opportunities across departments or with other organizations. |  | Project Implemented
| Create a SOP for MIS review that includes system continutiy, procuring, alinging systems, writing grants and re-occuring costs |  | SOP Completed
| Purchase a payroll program that is uniform for employees across all departments or enterprises. Create working group to evaluate needs of departments to be sure new system will be capable of doing what is needed. |  | Work group created, report containing needs written.
| Land Conservation Committee will research how other counties have combined Land Conservation with various other departments (e.g Zoning, Land Information, Waste and Recycling) and prepare a report to be presented to County Administration. |  | Report completed.
Improve Financial Practices | Improve the county’s bond rating by targeting improvement opportunities identified in Moody’s Rating Action of February 2020 and Rating Change of March 2018 |  | Maintain the existing Investment Grade rating for the county's general obligation debt, with improvement from A3 across a 5-year period | A2 Rating by 2025
| Create budget narratives summarizing how new initiatives or improvements implement the Strategic Plan |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Define value that could be added with 20% more funding, or lost due to a 20% reduction in funding |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Identify cuts that would not impact strategic planning goals or mandated services |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Identify how departments would respond to unexpected cuts or events |  | Achieve and maintain a general fund balance equal to 25% of annual operating expenses | Set target for 2022, 2023, 2024
| Develop a capital improvement plan inclusive of facilities, roads, and equipment |  | Project Implemented
| Analyze the county’s indirect rate to capture highest possible amount of grant funding, and establish a metric for productivity and efficiency |  | Increase non-tax revenue as a portion of overall revenue through grants and fees | Development of indirect rate by 2023. Maintain steady rate or lower annually
Annual list of grants applied for and received across all departments
Implement a Public Health review of financial decisions to recognize what, if any, the public health implications will be from decisions (e.g. well water study being cut).
| Increase discretionary and variable revenue source (fines, fees, grants, etc.) as a portion of the overall budget |  |  | Develop baseline data, and set metrics for annual improvement
Increase Coordination | Engage in joint procurement materials and equipment whenever possible |  | Develop list of materials for joint procurement
| Engage in joint contracting for capital projects to find savings resulting from reduced mobilization fees, increased competitive bidding, etc |  | Develop list of projects for joint contracting
Explore opportunities to share or contract staffing services
| Create additional and modern methods to communicate events and initiatives, and to generate direct input from the community. This could include community engagement via a new website or a social media presence |  | Development of new county website
| Coordinate community develop and land use decision-making in Richland Center among institutional partners such as Richland County, Richland Center, Richland Hospital, and Richland Local School District |  | Creation of a land use planning working group incorporating these organizations
Improve employee pay and HR policies | Obtaining market value for employee wages as determined through the county’s 2018 wage study |  | Meet the 2018 salary schedule commitments for county staff. | Market Value wages met by 2025
| Monitor the compensation and classification system for all positions to ensure positions remain market-competitive |  | Project Implemented | Market Value wages met by 2025
| Give annual pay raises |  | Project Implemented | Annual Pay Raises built in budgets
| Develop a uniform performance evaluation process that includes annual reviews, 6-month check-ins, and exit interviews |  | Develop baseline data on turnover, identify reasons for turnover, and reduce annual non-retirement and non-termination turnover | Set metric for annual turnover and targeted reduction if needed
| Develop a uniform set of human resources policies and procedures to improve transparency and accountability throughout the organization, including an update to the employee handbook and other related documents |  | Project Implemented
STRATEGIC PRIORITY: GROWTH
STRATEGY | TACTIC / ACTION | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Maintain investment in workforce and community development | Prioritize new home construction, and development using smart growth concepts. Smart growth planned economic and community development that attempts to curb urban sprawl and worsening environmental conditions |  | Year-over-year growth in new housing tied to county incentives/programs. | 2022 - incentives defined 2023 - 5-15 new homes developed as a result of county engagement
Encourage improvements to existingproperty to increase attractiveness
Support workforce development initiatives directed at attracting new residents
| Support and invest in broadband expansion throughout the county |  | Increase the number of county residents with high-speed internet | Annual growth in residents with Broadband Internet
Identify financially sustainable use options for the UW Richland campus
Evaluate sustainability of all non-mandated services
| Continue to invest in community and economic development partnerships with a demonstrated return-on-investment |  | Request annual return on investment reports from funded partners, and monitor to ensure ROI is steady or grwoing across multiple year periods | Annual delivery of ROI reports by funded partners. Annual steady ROI or ROI growth.
Support business attraction and retention | Develop a portfolio of incentives to support business growth
Identify priority areas in the county for future industrial, commercial, or residential development
Identify future land uses for county or municipal-owned land informed by economic opportunities and environmental constraints
Improve county identity and marketing | Collaborate with county partners in the development of a distinctive brand for Richland County that will serve to build a sense of identity and pride, and help attract new residents and tourists |  | Create a distinct Richland County brand and marketing platform targeted at tourists and workforce | Branding completed by 2022
| Create a new website that improve the county’s digital presence, and serves both an effective governmental function as well as serving as an attractive “front door” to the world for new businesses, residents, and tourists looking to discover the county |  | Create a new website | Website creation by 2023
| Capitalize on the county’s natural beauty and recreational opportunities through the investment and marketing of county parks, campgrounds, and recreational opportunities |  | Develop or update the county's outdoore recreation plan to guide investment and enable recreation grants | Plan updated by 2022
STRATEGIC PRIORITY: FOCUS
STRATEGY | TACTIC / ACTION | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Prioritize service of staffing | For each unmet existing service or new service being proposed, evaluate staffing needs using the following analysis |  | Develop process.
STRATEGIC PRIORITY: IMPROVEMENT
STRATEGY | TACTIC / ACTION | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
Develop a culture of support for employees | Celebrate success and the professional and personal achievements of employees. Recognize new hires, retirements, and year-of-service milestones. Build a culture that supports and celebrates its people |  | Develop parameters for this process, empower staff to lead
| Increase vacation time for new employees |  | Increased vacation for new employees | 2022 - research practices, develop and implement vacation policy 2023 - vacation policy implemented
| Evaluate flexible work schedules |  | Flexible work policy implemented | 2022-2023 - research practices, develop and implement flexible work policy 2024 - flexible work policy implemented
| Enable and empower departments to develop celebratory or team-building events. Day-long departmental retreats or other benefits can help build culture at a minimal expense |  | Develop parameters for departmental budgets. Submit with 2022 budget
Create a total benefits program for employees that highlights total compensation and investment of the county in its employees, inclusive of salary, fringe benefits, wellness, and professional development
| Encourage employee attendance and/or participation in professional development when appropriate. |  | Project Implemented | Procedures set up in 2022. Draft in 2023. Implemented by 2024
Improve Transparency of County Meetings | Adoption of iPads for use by Committees and boards, with folders for all meetings
Addition of meeting materials for all meetings on the county website
Development of a Listserv to automatically send agendas to the public and interested parties on a subscription basis
Addition of recordings from county board and committee meetings on the website
Invest in education of County Board Supervisors | Creation of a mentor program partnering tenured Supervisors with new Supervisors |  | Process Implemented
| Hold informal meetings with outgoing Supervisors and their successors to facilitate knowledge transfer |  | Process Implemented
| Fund new Supervisors’ attendance at annual Wisconsin Counties Association training or conferences |  | Process Implemented
| Create an on-boarding folder summarizing expectations for supervisors |  | Project implemented
| Support the attendance by new Supervisors at major Committee meetings, such as attending Finance Committee meetings during the annual budget development process. Create a mechanism to share agendas with all County Board Supervisors in order to facilitate this |  | Process explained and supervisors invited and empowered
RED Presentation to Board about what it means to develop community from wholistic standpoint (economic proficiency, community wealth and health).
| Support cross-training, collaboration, and peer learning between County Board Supervisors and their counter parts on the boards of outside partners, such as peer county boards, Neighborhood Services of Southwest Wisconsin, Southwest Wisconsin Community Action Program, Southwestern Wisconsin Regional Planning Commission, and the Southwest Wisconsin Workforce Development Board |  | Process explained and supervisors invited and empowered
| Conduct annual on-going training covering basic concepts of local government, such as the role of counties, county government finances, the role of county boards, elections, and departmental work |  | Process implemented | 2022 - establish training schedule 2023 - Begin implementing training
Deepen staff training in leadership and management | Sponsor department head training targeted at leadership and management, including Lean process training or UW Continuing Education certifications in Public Management or Human Resources |  | Process implemented | 2022 - Identify department heads looking for training, build into 2023 budget
Educate employees on how government works and the need for teamwork and partnership within county departments
Create a culture of sharing information and learning from peer counties
| Ensure conference attendance and professional development is aligned with the goals of the Strategic Plan |  | Process implemented | 2022 - Build this review into annual performacne evaluations, updating evaluation forms as needed and establishing procedures for evaluations if they don't exist.
On-going training or education targeted at the evaluation, adoption, and implementation of new technology to improve operational efficiency
Environment Stewardship and Resiliance
Create Comprehensive Plan
Process implemented

## Capital Facilities
LAST UPDATE: [INSERT DATE]
STATUTORILY REQUIRED SERVICES
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
County Jail and Sheriff's Office | LEJC will research and create a reocmmentation to County Administration in the next three years whether to construct a new facility or renovate the existing facility. | Improvement
| Analyze partnership opportunities in a new facilitiy or in the vacated existing space | Effectiveness
| Analyze land suitibility for a new facility in Richland Center or surrounding area | Effectiveness
County-wide Emergency Radio Towers | To be determined following study | Growth
Emergency Services Facility | Analyize feasibility of including the ambulance garage as a component of the possible jail builidng | Effectiveness
| Begin discussion and analyisis on the potential re-use opportunities for vacated space in the county courthouse | Effectiveness
Highway Improvement | Develop a plan for maintenance that needs to be done in order to save money in the long run. | Growth
| Take data laready in-hand for road status and create a plan that includes costs to implement yearly plan | Growth
DISCRETIONARY SERVICES
STRATEGY | TACTIC / ACTION | STRATEGIC PRIORITY | RESPONSIBLE PARTY | PERFORMANCE METRIC | PERFORMANCE TARGET | START DATE | END DATE (if applicable) | ESTIMATED FINANCIAL COST | STATUS
UW Richland | Improve the county's position relative to its relationship with the Board of Regents / UW Platteville and its ability ot make decisions about county property | Effectiveness
| Protect the county's investment in the UW Campus facilities through selective capital improvement investments, while halting all non-urgent capital improvements until a long-term use is determined | Effectiveness
| Determine with some certainty, the probability that a UW Richland Campus will exist in 2-4 years through the acquisition of UW Platteville's strategy for increasing enrollment at the UW Richland campus, including recruitment strategies, target populations, and distinct areas of study | Focus
| To reduce vacancy times in the event UW Platteville-Richland closes, develop scenarios for the use of these buildings and grounds in the event the relationship with the UW system ends, including a potential partnership with SWTC. | Growth
| Advocate to have UW-Richland to be an independent campus and not a satallite | Effectiveness
| Get the county out of campus food service provision | Focus
| Separate decisions about the agricultural land from decisions about the buildings. | Effectiveness
Symons Recreation Center | Maintain break-even, or net-positive, regurn on county operational and capital funding | Effectiveness
| Maintain facilities to ensur ethey stay relevant, modern, and distinct from other recreational facilities in the city | Effectiveness
| Evaluate the long-term liability to the county resulting from capital incestments or expansion plans | Focus
| Evaluate whether this service could be successful if owned and managed by other partners, and make plans ot divest the county of ownership of this facility | Focus
| Evalute the impact of future expansion plans on capital and operational expenses and the county's bond rating | Effectiveness
| Consider assisting with marketing and membership if it can assist with the transfer of ownership | Effectiveness
Tri-County Airport | Reduce or eliminate flood risk to the airport, hangers, and other faciliites | Effectiveness
| Ensure the long-term viability of this asset to support ocunty economic development efforts | Growth
| Develop an evaluation process to monitor continued return on investment to the county | Improvement
Pine Valley Community Village | Protect the county's investment through funded maintenance of an on-going capital investment plan funded by Pine Valley Revenues | Effectiveness
| Monitor return on investment of the facility, and have revenue to cover 50% of debt service tied to the 2016 improvements as per the terms of bond sale on 3/1/2016 | Improvement
| Develop a process for evaluating future demand, adjust for impacts to healthcare funding, population growth, and demographic changes in the county | Improvement
| Evalute whether management, financial, operational changes could occur to reduce the impact of owning and opeating this facility on the county's bond rating | Effectiveness